## Summary
UAT summary - Complaint handling redesign
Test cases executed | 25
Passed in cycle 1 | 20
Failed in cycle 1 | 5
Passed after retest | 25
Defects raised | 5
Open critical / major defects | 0
Exit criteria met | Yes

## Test cases
Test ID | Title | Requirement | User story | Preconditions | Steps | Expected result | Cycle 1 | Cycle 2 (retest) | Defect ID
TC-01 | Valid customer number auto-fills customer data | FR-01 | US-01 | Customer 100245 exists in SAP QA | Create complaint; enter customer no. 100245 | Name, country, account manager, type filled and read-only | Pass | -
TC-02 | Invalid customer number rejected | FR-01 | US-01 | - | Enter customer no. 999999; click Save | 'Customer not found in SAP'; record not saved | Pass | -
TC-03 | Valid material code auto-fills material data | FR-02 | US-02 | AS-4410-22 active in SAP QA | Enter material code AS-4410-22 | Description, product family 'Air springs', plant filled | Pass | -
TC-04 | Obsolete material triggers warning | FR-02 | US-02 | Material BC-2001-05 status obsolete | Enter material code BC-2001-05 | Warning shown; user must confirm to continue | Fail | Pass | DEF-01
TC-05 | Save blocked when batch number missing | FR-03 | US-03 | - | Complete all mandatory fields except batch; click Save | Not saved; batch field highlighted with message | Pass | -
TC-06 | Save succeeds with all mandatory fields | FR-03 | US-03 | - | Complete all mandatory fields; click Save | Record saved; complaint ID generated | Pass | -
TC-07 | Defect picklist filtered by product family | FR-04 | US-04 | Product family 'Brake chambers' | Open defect code list | Only brake-chamber defect codes listed | Fail | Pass | DEF-05
TC-08 | Free text not accepted as defect code | FR-04 | US-04 | - | Type a new value into defect code field | Value rejected; free text only in description | Pass | -
TC-09 | Duplicate customer reference warning | FR-05 | US-05 | CMP-01200 exists with ref QN-55871 | Register new complaint, same customer and reference | 'Possible duplicate of CMP-01200'; Link / Continue | Pass | -
TC-10 | Auto-assignment for mapped product family | FR-06 | US-06 | Air springs mapped to Assembly Line 2 | Log first response on an air-spring complaint | Assigned to Assembly Line 2 owner and engineer | Pass | -
TC-11 | Unmapped product family goes to team lead queue | FR-06 | US-06 | Test family with no owner | Log first response | Case appears in team lead queue | Pass | -
TC-12 | Reminder at 1 day without first response | FR-07 | US-07 | Complaint received Mon 09:00 | Advance test clock to Tue 09:00 | Reminder e-mail to assigned engineer | Pass | -
TC-13 | Escalation at 1.5 days without first response | FR-07 | US-07 | Engineer reassigned after creation | Advance test clock to Tue 21:00 | Escalation e-mail to the current engineer's team lead | Fail | Pass | DEF-02
TC-14 | Cannot enter D5 without verified root cause | FR-08 | US-08 | Case in D4, root cause not verified | Move case to D5 | Blocked with message | Pass | -
TC-15 | Closure requires D8 fields and customer confirmation | FR-08 | US-08 | Case in D8 | Close case without customer confirmation | Closure blocked until confirmation recorded | Pass | -
TC-16 | Overdue corrective action notification | FR-09 | US-09 | Action due yesterday, open | Run daily alert job | Action owner and department owner notified | Pass | -
TC-17 | Credit note EUR 1,500 routed to team lead only | FR-10 | US-10 | - | Request credit note EUR 1,500 | Single approval step: team lead | Pass | -
TC-18 | Credit note EUR 4,800 routed to QM then Finance | FR-10 | US-10 | - | Request credit note EUR 4,800 | Two steps: Quality Manager, then Finance Controller | Pass | -
TC-19 | Rejected credit note returns with mandatory comment | FR-10 | US-10 | Request pending with team lead | Reject without comment; then with comment | Blocked without comment; returned to requester with comment | Pass | -
TC-20 | Approval audit trail recorded and locked | FR-11 | US-11 | Approved credit note | Open audit trail; try to edit as admin | Approver, timestamp, decision, comment shown; edit not possible | Pass | -
TC-21 | Approved credit note in SAP hand-off file | FR-12 | US-12 | Two approvals today | Generate daily hand-off file; import in SAP QA | Two rows; dot decimal; import succeeds | Fail | Pass | DEF-03
TC-22 | Weekly KPI extract reconciles with case list | FR-13 | US-13 | Test week with 60 cases, 2 reopened | Run weekly extract; compare with case list | All KPI figures match case list | Fail | Pass | DEF-04
TC-23 | Attach three photos up to 10 MB | FR-14 | US-14 | - | Attach 3 photos (4, 8, 10 MB) | All attached and visible to assigned engineer | Pass | -
TC-24 | Engineer role cannot approve credit notes | NFR-02 | US-10 | User with engineer role | Open pending credit note | Approve/Reject buttons not available | Pass | -
TC-25 | SAP look-up response time | NFR-01 | US-01, US-02 | Business hours, 20 look-ups | Time customer and material look-ups | 95% of look-ups within 2 seconds | Pass | -

## Defect log
Defect ID | Test ID | Description | Severity | Status
DEF-01 | TC-04 | Obsolete material accepted without warning (status field not mapped) | Major | Fixed - retest passed
DEF-02 | TC-13 | Escalation sent to original engineer's lead after reassignment | Major | Fixed - retest passed
DEF-03 | TC-21 | Hand-off file used comma decimal separator; SAP import rejected rows | Critical | Fixed - retest passed
DEF-04 | TC-22 | Reopened cases counted twice in weekly received volume | Major | Fixed - retest passed
DEF-05 | TC-07 | Two retired defect codes still shown for Brake chambers | Minor | Fixed - retest passed